## Project Planner
Laurence's Plan for Remaining PhD Work
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
[6 empty] | JULY |  | AUGUST |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH
WEEKS
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Complete MTT paper | 1 | 2 | 0 | 0 | 0% | bar: WEEKS 6
Draft Introduction Chapter | 1 | 2 | 0 | 0 | 0% | bar: WEEKS 6
Meas. for FD NL Meas. Paper | 3 | 1 | 0 | 0 | 0% | bar: WEEKS 6
Write FD NL Meas. Paper | 3 | 2 | 0 | 0 | 0% | bar: WEEKS 6
Draft Measurement Uncertainty Chapter | 3 | 2 | 0 | 0 | 0% | bar: WEEKS 6
Meas. for XP Extract Opts. Paper | 5 | 1 | 0 | 0 | 0% | bar: WEEKS 6
Write XP Extract Opts. Paper | 5 | 3 | 0 | 0 | 0%
Draft Microwave Meas. Unc. Chapter | 5 | 3 | 0 | 0 | 0% | bar: WEEKS 6
Draft NL Microwave Meas. Unc. Chapter | 5 | 2 | 0 | 0 | 0% | bar: WEEKS 6
Draft NL Behavioural Modelling Chapter | 8 | 2 | 0 | 0 | 0% | bar: WEEKS 6
Draft NLBM Meas. Uncertainty Chapter | 10 | 2 | 0 | 0 | 60% | bar: WEEKS 6
Draft Conclusion | 12 | 2 | 0 | 0 | 0% | bar: WEEKS 6
Reviews | 14 | 3 | 0 | 0 | 50%
Submission | 17 | 1 | 0 | 0 | 0%
Potential Further Applications Chapter | 0 | 0 | 0 | 0 | 0%